## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Dissemination activities
Milan Gocić
Slaviša Trajković
University of Niš
PMC meeting/09 May 2019

## Slide 2: Visibility of the EU and the Erasmus+ Programme
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
European emblem (the 'EU flag') and the name of the European Union spelled out in full in all communication and promotional material and with the following text 'Co-funded by the Erasmus+ Programme of the European Union' next to the EU emblem

## Slide 3: Disclaimer
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Disclaimer shall be added to the inner pages of the publications
"The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsi­ble for any use which may be made of the information contained therein."

## Slide 4: Dissemination plan
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dissemination plan determines
objectives,
target groups,
key messages,
strategy,
activities,
methods,
overall dissemination time plan,
evaluation of dissemination.

## Slide 5: Target groups
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
students of bachelor studies related to WRM
WB teaching staff
representatives of bodies and agencies for WRM
engineers from non-academic and water sectors in WB countries.

## Slide 6: Key messages
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Water resources became the greatest global challenge and an indispensable requirement for sustainable development
New educated professionals in the field of water resources management
New LLL courses for enhancing the skills of personnel in water sector contributes to use new and innovative methods in solving problems in water sector

## Slide 7: Key words
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Strengthening of educational base: modern curriculum, harmonization, competencies, Bologna, interdisciplinary, innovative, master, innovative learning
Enhancing professionals’ in water sector awareness and skills: drinking water, pollution, sewage, purification, watershed, lack of water, water shortage, discharge, drainage, irrigation, irrigation, lifelong learning, trainings, skills

## Slide 8: Dissemination activities
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of project website and promotional materials
Info days for student enrolment (one per WB HEI)
Roundtables with non-academic sector (one per WB HEI)
Winter/summer schools (one school per EU HEI)
Symposium for promoting WRM in WB (Novi Sad, 2021)

## Slide 9: A6.2 Development of project website and promotional materials
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
The project website was created and will be regularly maintained and updated. Information will be presented in all partners’ languages.
Promotional material (bag, leaflet, project brochure, pencil, folder, poster, roll-up) including visual identity was designed and printed.
The activity will be organized through the entire project
Outcome: Promotion material created
Due date: 14-11-2021

## Slide 10: A6.3 Info days for student enrolment
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Seven info days for promotion enrolment of master students will be performed in the WB HEIs (covering consortium partners and the other related HEIs). The promotional materials for student enrolment will be delivered to inform future students about newly developed curricula.
Second project year
Outcome: Info days organized
Due date: 14-10-2020

## Slide 11: A6.4 Roundtables with non-academic sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Seven roundtables with participation of non-academic sector will be organised for the promotions of trainings for professionals in water sector by WB HEIs staff. The promotional materials regarding SWARM project and trainings will be delivered to all interested parties. PWMCVV and associated partners from water sector will take participation and help WB HEIs in organisational activities.
Activity from the second project year
Outcome: Roundtables organized
Due date: 14-11-2020

## Slide 12: A6.5 Winter/summer schools
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
The students’ short-time mobility from WB to EU partner HEIs is planned. Three winter (January 2021 – UL and AUTH, February 2021 – UNIRIFCE) and three summer schools (June 2021 – NMBU and BOKU, July 2021 – UACEG) in duration of 5 days will be organized with a participation of 13 WB students per school.
The activity will be organized during the third project year.
Outcome: Winter/summer schools organized
Due date: 14-09-2021

## Slide 13: A6.6 Symposium for promoting WRM in WB
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Symposium for promoting water resources management in WBs will be organized in the third project year by UNS in July 2021. Participants from the partner institutions (24 teaching staff) will prepare and present their research.
Activity from third project year
Outcome: Report on organized Symposium
Due date: 14-08-2021

## Slide 14: Dissemination tools
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
SWARM website and social media such as Instagram and Facebook (used for online dissemination)
project publications and promotional materials such as flyer, brochure, poster, videos, newsletters, newspapers’ and magazines’ articles (used for offline dissemination)
dissemination events at institutional, country or regional level with possible participation of external stakeholders

## Slide 15: SWARM templates
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Annex DE1 – Word document template
Annex DE2 – Power Point presentation template
Annex DE3 – Dissemination activity form
Annex DE4 – Newsletter template

## Slide 16: Sustainability
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
WB HEIs will continue to implement the developed master curricula
The formed LLL courses for professionals in water sector will be offered to all interested stakeholders
WB HEIs will continue to maintain the formed laboratories and the new teaching environment